## Business
Phase | Task | Subtask | Hours Needed | Owner | Status
1. Research and Planning | Research about Polymarket | Study on Polymarket as decentralized platform and gap identification | 60 | B1, B2
|  | Use case on how prediction market outperform traditional risk transfer methods | 60 | B1, B2
| Define Project Scope | Prototype operation model design for binary predictive market | 30 | B1,B2
|  | Estimation on SDLC | 20 | T1
| Identify Target Audience | User identification in politics, sports, crypto events, etc., which are niche opportunities in underserved markets | 25 | B1,B2
|  | Institutional application exploration | 25 | B1,B2
| Competitior Analysis | Study about Polymarket, Kalshi, Augur for multiple features, including yes/no betting, liquidity pools, resolution mechanism | 60 | B1,B2,H
| Legal Requirement Analysis | Regulation research, including but not limited to gambling law, KYC/AML | 70 | B1,B2
| Technical Research | Study on Blockchain | 50 | B1,B2
|  | Study on Smart Contract | 50 | B1,B2
|  | Study on security measures | 50 | B1,B2,T1
| Cost Analysis | Budget for technical development | 20 | B2
2. Report Writing | Report Writing | Summarize the research | 160 | B1,B2,H,T1,T2
|  | Provide insights on the risk transfer model of prediction market | 160 | B1,B2,H,T1,T2
|  | Report checking and finalization | 20 | B1,B2
3. Deployment and Launch | Market the Platform | Promote on social media | 20 | B1,B2
|  | Build community via Discord, Twitter and forums | 20 | B1,B2
|  | Total | 900
Business Role 1 | Researcher, UI/UX Designer, End User, Business Analyst, Tester | 315.6667
Business Role 2 | Researcher, Project Manager, End User, Business Analyst, Tester | 335.6667
Hybrid Role | Researcher, Business Analyst, Developer, Tester | 84
Technical Role 1 | Project Manager, Business Analyst, Tester, Developer | 100.6667
Technical Role 2 | Solution Architect, Full Stack Developer, Tester | 64

## Technical
Phase | Task | Subtask | Hours Needed | Owner | Status
0. Preparation | Study | Study Blockchain, including Etherum | 90 | Developer (T1,T2, H) | In Progress
|  | Study Solidity for Smart Contract | 90 | Developer (T1,T2, H) | To be started
|  | Study Chainlink, UMA for real-world data fetching to resolve market | 90 | Developer (T1,T2, H) | To be started
| Tools | Install all relevant tools and study the relevant frontend and backend programming language | 30 | Developer (T1,T2, H) | Completed
1. Planning | Scope Definition |  | 20 | Business Analyst (T1, H), End User (B1, B2) | In Progress
| Requirement Gathering | Features to be developed | 20 | Business Analyst (T1, H), Developer (T2) | To be started
| Waterfall Project Planning and Management | Timeline Establishment | 15 | Project Manager (T1, B2) | In Progress
|  | Resources Allocation | 15 | Project Manager (T1, B2) | In Progress
2. Analysis | User Story | User Story Creation | 20 | Business Analyst (B1,B2,T1, H) | To be started
|  | User Story Grooming | 20 | Business Analyst (B1,B2,T1, H), Developer (T2) | To be started
3. Design | High-level Architecture Design |  | 15 | Solution Architect (T2) | To be started
| Technical Solution Design |  | 15 | Solution Architect (T2) | To be started
| UI/UX Design | Figma Prototype | 30 | Designer (B1) | To be started
4. Implementation | Web development for reporting |  | 30 | Developer (T1,T2) | To be started
| Backend development for prototype | Integration with Blockchain | 20 | Developer (T1,T2,H) | To be started
|  | Decentralize file storage development through IPFS | 25 | Developer (T1,T2,H) | To be started
| Order Management Lifecycle Implementation | Hybrid Central Limit Order Book (CLOB) for off-chaim matching and on-chain execution | 30 | Developer (T1,T2,H) | To be started
| Smart contract development | Contract creation with Gnosis Conditional Token Framework for core logic | 30 | Developer (T1,T2,H) | To be started
|  | Create Solidity contract where users define events | 40 | Developer (T1,T2,H) | To be started
|  | Function implementation for buying/selling shares using ERC-1155 tokens, collateralized by USDC | 50 | Developer (T1,T2,H) | To be started
| Web development for prototype | React app creation | 25 | Developer (T1,T2,H) | To be started
|  | Responsive application | 8 | Developer (T1,T2) | To be started
|  | Integration with Backend through user sessions or API calls | 50 | Developer (T1, T2) | To be started
|  | Integration with Automated Market Makers (AMM) for dynamic pricing and liquidity | 60 | Developer (T2) | To be started
| MetaMask wallet setup for getting testnet ETH from faucets for testing phase |  | 25 | Developer (T2) | To be started
5. Testing and Integration | Test Case Writing |  | 20 | Tester (T1, H) | To be started
| Test Case Review |  | 10 | Tester (T1, H) | To be started
| Unit Testing | Testing the modules individually with Mocha/Chai and Ganache for local blockchain simulation | 40 | Developer (T2) | To be started
| Integration Testing | Testing on the interaction between individual componenet | 55 | Tester (T1, H) | To be started
| End-to-End System Integration Testing (E2E SIT) | Testing E2E functionality on Polyhon/ Ethereum Testnet | 55 | Tester (T1, H) | To be started
| User Acceptance Test (UAT) | End user testing on Polygon/ Ethereum Testnet | 55 | End User (B1, B2) | To be started
| Performance Testing | Evaluate the speed, responsiveness and stability of the prototype in handling high volume trading | 25 | Tester (T1,H) | To be started
| Sanity Test | Testing on specific bug fix/ minor change of work | 40 | Business Analyst (B1,H) | To be started
| Regression Test | Re-runs of the critical test cases to ensure code changes does not affect any existing functionality | 40 | Tester (B1,B2,T1, H) | To be started
6. Deployment | Beta-Testing |  | 30 | End User (B1, B2) | To be started
| Pilot Launch |  | 8 | Business Analyst (T1, H), Developer (T2), End User (B1, B2) | To be started
7. Maintenance |  |  | 0 |  | To be started
|  | Total | 1241
Business Role 1 | Researcher, UI/UX Designer, End User, Business Analyst, Tester | 118.1
Business Role 2 | Researcher, Project Manager, End User, Business Analyst, Tester | 83.1
Hybrid Role | Researcher, Business Analyst, Developer, Tester | 338.1
Technical Role 1 | Project Manager, Business Analyst, Tester, Developer | 347.1
Technical Role 2 | Solution Architect, Full Stack Developer, Tester | 384.6

## Total
Role | Responsibility | Business Hours | Techincal Hours | Total
Business Role 1 | Researcher, UI/UX Designer, End User, Business Analyst, Tester | 315.6667 | 118.1 | 433.7667
Business Role 2 | Researcher, Project Manager, End User, Business Analyst, Tester | 335.6667 | 83.1 | 418.7667
Hybrid Role | Researcher, Business Analyst, Developer, Tester | 84 | 338.1 | 422.1
Technical Role 1 | Project Manager, Business Analyst, Tester, Developer | 100.6667 | 347.1 | 447.7667
Technical Role 2 | Solution Architect, Full Stack Developer, Tester | 64 | 384.6 | 448.6